## Defect
Defect ID | Defect Description | Steps to Reproduce | Actual Result | Exp Result | Severity | Priority | Raised By | Defect Raised Date | Assigned To | Root Cause | Fix Applied | Status
DEF_001 | In the Profile management ,while editing the personal details name change is getting reflected in the profile but not getting reflected in the dashboard in the navbar | Step 1: Open online banking system url “http://users/2858441/Documents/UI/customer.html” Step 2: Click on edit Step 3. Update the name of the Customer Step 4: Click on Save button | Updated name is not displayed in the navbar | After updating the name , it should be reflected in the navbar too | Low | High | Rahul | 2026-01-16 | Gowthami | Using a wrong variable | Modified the variable in the dashboard to get updated along with the edited details | Closed
DEF_002 | In PDBC while registering the password constraint is just the length of 4 , not meeting the actual password requirements | Step 1: Run "python main.py" Step 2: Choose Register(1) Step 3: Enter Registration details which are required Step 4: Enter password of length 3 Step 5: Click Enter | Password is not of lenght 4 | Password should have atleast one Upper case , One Lower case, One number , One Special charcter ,Password Length must be of greater than 12 characters | High | High | Vamsi | 2026-01-16 | Praneeth | Validation is not properly Done | Did the proper Validation and resolved | Closed
DEF_003 | In the Policy management Page , Total Coverage is given as dollars , It shoud be in INR | Step 1: Open online banking system url “http://users/2858441/Documents/UI/customer.html” Step 2: Go to Policy Management | The Total Coverage is Displayed as Dollars | The Total Coverage should be in INR | Low | Low | Akhil | 2026-01-16 | Bhavish | Did not check for the Currency Icon | Total Coverage amount Changed to INR , displayed as INR | Closed
DEF_004 | Mapping of Agent ID is not working from assignment table to claims table | Step 1: Run "python main.py" Step 2: Login as admin and go to admin dashboard Step 3: Choose assigning claims to agent Step 4: After assigning GOTO claims table and see the agent ID,Agent is NULL | Agent id is not getting reflected in claims table | Agent id should be reflected in Claims table | High | High | Chinranjeevi | 2026-01-16 | Aravind | While Integrating , Updating query for the claims table is missing | Added that updating query for the claims table | Closed